## Project Info
PROJECT GANTT CHART TEMPLATE
Project Info › Tasks › Gantt › Holidays – everything is linked; fill the yellow cells only
PROJECT DETAILS |  | SCHEDULE HEALTH (auto-calculated)
Project Name | Website Redesign & Launch | Planned Finish (baseline)
Client Name | Acme Corporation | Forecast Finish (incl. delays)
Project Manager | Your Name | Target Completion Date
Project Code / Reference | PRJ-2026-001 | Delay vs TARGET (working days)
Project Start Date | 2026-10-05 | Delay vs PLAN (working days)
Target Completion Date | 2026-12-18 | Overall % Complete (duration weighted)
Status (Report) Date | 2026-11-06 | Calendar days late vs Target
Gantt View (set on Gantt sheet)
TASK STATISTICS |  | HOW TO USE
Total Tasks |  | 1. Fill the yellow Project Details (start, target, report date).
Completed |  | 2. Holidays sheet: list non-working dates. Sat/Sun are automatic.
In Progress |  | 3. Tasks sheet: type Task Name + Duration (working days) + up to 2 predecessor IDs. Dates are calculated.
Not Started / On Hold |  | 4. Update progress: Status, Actual Start/End, % Complete. Use Revised Duration if you expect an overshoot.
Tasks Overshooting Duration |  | 5. Gantt sheet: pick Day / Week / Month in cell B2; scroll the timeline with C2.
Tasks Affected by Others' Delay |  | 6. 300 task rows are pre-built; copy the last row down to add more.
Largest Overshoot (task) |  | 7. Predecessor = Finish-to-Start (starts next working day after it ends). Avoid circular links.
Total Planned Task-Days |  | Yellow cells = input · white cells = formulas (do not overwrite).
COLOUR LEGEND
Completed | Task finished (bar portion within plan)
In Progress | Task started, not finished
Not Started | Scheduled, not yet begun
On Hold | Task paused
Overshoot | Time used beyond the planned DURATION (task ran / is expected to run over)
Delayed / Affected | Start pushed out by a late predecessor or by the status date (see 'Impact' column)
Planned (not used) | Planned time no longer used (finished early / started late)
Weekend | Saturday / Sunday (Day view)
Holiday | Dates from the Holidays sheet (pink header in Week/Month view = holiday inside period)
Status Date | Column of the report date set on Project Info
▶ Start | First day of a task with no predecessor
↳ Dependent start | First day of a task that waits for a predecessor
◀ End | Last day of a task
➜ End feeds others | Last day of a task that other tasks depend on
◆ Start = End | Task starts and ends in the same period
Note on C11: Date up to which progress is reported. Enter =TODAY() to track live. Un-started tasks cannot start before this date and in-progress tasks are measured against it.

## Tasks
Type in the YELLOW cells only. Columns M–V calculate by themselves. Predecessor = ID of the task that must finish first (up to 2). Duration is in WORKING days (weekends & holidays skipped).
① TASK ENTRY | [6 empty] | ② STATUS UPDATE |  |  |  |  | ③ SCHEDULE & ANALYSIS (automatic) | [9 empty] | helper
ID | Task Name | Owner | Predecessor 1 (ID) | Predecessor 2 (ID) | Duration (work days) | Start No Earlier Than (optional) | Status | Actual Start | Actual End | % Complete | Revised Duration (if overshoot) | Planned Start | Planned End | Forecast / Actual Start | Forecast / Actual End | Forecast / Actual Duration | Duration Variance (days) | Duration Status | End Slip vs Plan (days) | Impact (affected by) | No. of Dependent Tasks | class | has pred | pred1 slip | pred2 slip | eff status | eff % | end if no overshoot
| Project Kickoff & Charter | Project Manager |  |  | 2 |  | Completed | 2026-10-05 | 2026-10-06 | 100%
| Requirements Gathering | Business Analyst | 1 |  | 5 |  | Completed | 2026-10-07 | 2026-10-15 | 100%
| Technical Architecture | Architect | 2 |  | 4 |  | Completed | 2026-10-16 | 2026-10-21 | 100%
| UX Wireframes | UX Designer | 2 |  | 10 |  | In Progress | 2026-10-16 |  | 70% | 17
| Visual Design | UI Designer | 4 |  | 8 |  | Not Started
| Database Setup | DBA | 3 |  | 5 |  | Completed | 2026-10-22 | 2026-10-30 | 100%
| Backend API Development | Dev Team A | 6 |  | 12 |  | In Progress | 2026-11-02 |  | 30%
| Frontend Development | Dev Team B | 5 | 6 | 10 |  | Not Started
| Content Creation | Content Lead | 2 |  | 10 | 2026-10-26 | In Progress | 2026-10-26 |  | 80%
| Integration & QA Testing | QA Team | 7 | 8 | 8 |  | Not Started
| User Acceptance Testing | Client | 10 |  | 5 |  | Not Started
| Training & Documentation | Trainer | 9 |  | 5 |  | On Hold
| Deployment / Go-Live | DevOps | 11 | 12 | 2 |  | Not Started
| Project Closure & Handover | Project Manager | 13 |  | 2 |  | Not Started
Formulas:
Planned End = IF(OR([Planned Start]="",NOT(ISNUMBER([Duration (work days)]))),"",WORKDAY([Planned Start],MAX(1,[Duration (work days)])-1,Holidays!$A6:A205))
Forecast / Actual End = IF(OR([Forecast / Actual Start]="",[Forecast / Actual Duration]=""),"",IF(ISNUMBER([Actual End]),[Actual End],WORKDAY([Forecast / Actual Start],[Forecast / Actual Duration]-1,Holidays!$A6:A205)))
Forecast / Actual Duration = IF(OR([Forecast / Actual Start]="",NOT(ISNUMBER([Duration (work days)]))),"",IF(ISNUMBER([Actual End]),MAX(1,NETWORKDAYS([Forecast / Actual Start],[Actual End],Holidays!$A6:A205)),MAX(1,IF(ISNUMBER([Revised Duration (if overshoot)]),[Revised Duration (if overshoot)],[Duration (work days)]),IF(ISNUMBER([Actual Start]),NETWORKDAYS([Actual Start],N('Project Info'!$C11),Holidays!$A6:A205),0))))
End Slip vs Plan (days) = IF(OR(NOT(ISNUMBER([Planned End])),NOT(ISNUMBER([Forecast / Actual End]))),"",IF([Forecast / Actual End]>=[Planned End],NETWORKDAYS([Planned End],[Forecast / Actual End],Holidays!$A6:A205)-1,-(NETWORKDAYS([Forecast / Actual End],[Planned End],Holidays!$A6:A205)-1)))
end if no overshoot = IF(OR([Forecast / Actual Start]="",NOT(ISNUMBER([Duration (work days)]))),"",WORKDAY([Forecast / Actual Start],MAX(1,[Duration (work days)])-1,Holidays!$A6:A205))

## Gantt
| Week | 0 |  | ◀ pick Day / Week / Month · Scroll = shift timeline by n periods (+ later / − earlier)
LEGEND ▸ bar colour = task status · RED part of a bar = time over the planned duration | [9 empty] | Completed | In Progress | Not Started | On Hold | Overshoot (over duration) | Delayed / Affected | Planned, unused
Orange task name = delayed by predecessor · Red task name = duration overshoot · Pink header = holiday | [9 empty] | Weekend | Holiday | Status date | ▶ Start | ↳ Starts after pred. | ◀ End | ➜ End feeds others | ◆ Start = End
TASK SCHEDULE (Plan vs Forecast / Actual)
ID | Task | Depends On | Plan Start | Plan End | Fcst / Actual Start | Fcst / Actual End | Status | % Done | Var (days)

## Holidays
HOLIDAY LIST
Enter one non-working date per row (yellow cells). Saturdays and Sundays are always treated as weekends automatically. Holidays shift task dates and are shaded pink on the Gantt chart. Delete or overwrite the sample rows.
Holiday Date | Holiday Name | Day
2026-10-20 | Sample holiday 1 (edit me)
2026-11-10 | Sample holiday 2 (edit me)
2026-12-25 | Christmas Day